## Major Projects (hidden)
Project & approved budget | PM and | Deliverables achieved this period | Deliverables due next period | Status | Explanation / mitigation | LT action | Finance
| Project Sponsor | [5 empty] | Spend to date
Pinehurst Community Centre refurbishment | Geoff Hayden | EHDC and CVS working with the residence association to become a formal legal entity, so that an agreement for lease can signed | Signed lease in place |  | If the refurbishment options chosen require planning permission or the residents association want to apply for external match funding to increase the budget, this window will be missed and works will try to be programmed in to cause the least disruption to the continued use of the Centre. | NO
250000 | Bob Palmer | Measured building survey being undertaken, with consultant confirming what improvement options are available. | Measured survey produced and improvement options considered |  | Project funding and authority is unknown at this time. Further authority report is required to secure a budget following the termination of the Kingsmead Project. Budget will include a mix of EHDC funding and S.106 funding
Aiming for the refurbishment window of the summer holidays when the children’s centre is closed
Hertford Hydro | David Thorogood | Meetings held with EA and Hertford Theatre team determined that joint Flood Risk Assessments not required. Hertford Theatre works have been pulled back from the river edge, so project construction no longer needs to be coordinated. Hydro project to move ahead independently | Updated Flood Risk Assessment and hydraulic designs for new planning application |  | Continuing to develop information for full submission | NO | 26622
Jonathan Geall
211000
Hartham Leisure Centre | Emily Coulter | Planning permission deferred at DMC in January | Review period being undertaken |  | Planning deferred due to issues with design / massing and sustainability | NO | 620997
| Jess Khanom |  |  |  | S257 application to be applied for during review period
8746000 |  |  |  |  | Risk assessment of Hartham roof to be undertaken during review
Plus
£950,000 (sustainability)
Grange Paddocks | Emily Coulter | Planning permission granted in November. | Contract for RIBA stages 4-7 agreed and technical design commences. |  | Construction risks for the leisure centre will be outlined to key services in an Executive summary of the delivery agreement. A contingency allowance has been retained. | NO | 1613861
23221939 | Jess Khanom | EA permit achieved for temporary bridge. | Start of construction phase |  | 3G pitch site continues to be explored through consulting the EA and understanding trees on the site. Geo-tech surveys to be considered for the site.
Plus
£50,000 (sustainability) |  | Final cost agreed for leisure centre construction contract, with contracts to be formalised in the next 3 weeks. | Planning permission submitted for the 3G pitch
Old River Lane | Ian Pennington | Approval of Investment Options by Council | Agree approach and roles and responsibilities for commercial negotiations and Development Agreement production. |  | Future state traffic modelling will be produced to inform ongoing discussions with HCC Highways. | NO | No spend to date
30000000 | Richard Cassidy | Initial approach memo produced for commercial negotiations and Development Agreement production. | Agree broad model of governance for the ORL Arts Centre |  | These discussions will establish the viability of the fourth junction that will allow for access to the reformatted Waitrose Carpark, and failure to achieve this will impact the design and fulfilment of objectives of the scheme.
|  |  | Agree library inclusion with the ORL scheme. |  | Rerouting of a mains sewer and branch pipe has been established as the most feasible solution to overcome impact to scheme and initial costs have been estimated at £1m.
Additional works will now take place to define these costs further.
Future planning process timeline will now be informed by the DV and commercial negotiations.
Northgate End | Ian Pennington | JCT (Contractors contract) has been agreed. | Profiling and contract amendment for LEP funding to be complete – Awaiting schedule from Rydons to inform. |  | Carpark closure and initial comms have been produced. | NO | 3112598
19033000 |  | Engrossments and main lease agreed with HCC. |  |  | April 20th is set for closure with site decommissioning taking place and the establishment of site accommodation, temp works and prelims.
Watching brief surveys are taking placed on site on the 3rd of March to establish extent of works that can take place and then to inform site schedules moving forward.
Hertford Theatre | Tamara Jarvis | RIBA stage 2 has been signed off and RIBA stage 3 commenced. Site investigation (geotechnical) surveys being carried out. Successful meetings with Historic England and Environment Agency | Asbestos and culvert surveys to be carried out in March. Project Board and Reference Group meetings to share next iteration of designs |  | Programme on track. Project risks remain but with mitigating actions in place | NO | 316838
Design Review Panel and Formal Planning pre app meetings in March
£19.900,000 | Jess Khanom
Castle Park | Ian Sharratt | Successful community archaeological dig in October. Good finds and support from community | Consultant now drawing up tender documents for all principal works |  | Programme on track. Project risks remain but with mitigating actions in place | NO | 29155
Relocation of tennis courts – planning application approved - see risks
2537800 | Jess Khanom | Bat surveys complete | Building designs being reviewed in relation to sustainability in response to recent climate agenda |  | Development Control have revised their guidance as part of the Grange Paddocks Leisure Centre build project to require the courts to be located further north in the old town tip area but grouped together with the proposed 3G football pitch. This has created some difficulty in fitting both improvements into the space without compromising a nearby drainage channel and adjacent trees. Solutions currently being explored by leisure centre consultants.
Expansion of community events programme
|  | First phase of tree works completed. | Considering change to air source heat pumps
Project Management Consultancy Contract agreed by NLHF and awarded.
Contract to design conservation works to restore Castle Remains awarded
Design Interpretation Contract awarded to create signage and notice boards
Café tender being drafted for occupation April 2021.
Landscape designs under final review
HUDs | Tamara Jarvis | ETRO period being extended to May to allow for further monitoring in response to public feedback | Assessment of monitoring to be undertaken |  | Additional monitoring is being undertaken in response to resident feedback but no formal objections have been received which would prevent PTO being commencing | NO | 990400
Final street cleansing taken place
975000 | Sara Saunders |  | PTO to be drafted and advertised
Buntingford Depot infrastructure work | Geoff Hayden | EA provided verbal agreement to the permit application following adjustments to the Fire Prevention Plan | Works to connect the CCTV to the Hertfordshire CCTV Partnership Monitoring station in Stevenage is still progressing, IT looking into independent fibre broadband connection so that the system in not affected by usage on our fibre network at the depot |  |  | NO | 8000
225000 | Jess Khanom | Works commenced for the foul drainage improvements and water supplies – should be complete in 3 weeks
Works to connect the CCTV to the Hertfordshire CCTV Partnership Monitoring station in Stevenage progressing, IT looking into independent fibre broadband connection so that the system in not affected by usage on our fibre network at the depot
Harlow and Gilston | Sara Saunders | Application from places for people submitted 17 May for: | Planning determination to be agreed |  |  | NO
1. Outline Planning Permission with all matters reserved apart from external vehicular access for a mixed use development of up to 8,500 homes for a part of the Gilston Area
2. Detailed Planning Permission for: alterations to the existing Fifth Avenue bridge
erection of a new road, pedestrian and cycle bridge Listed Building Consent for works to Fiddlers Brook Bridge

## Jan 2022
On a monthly basis, this Action Plan is updated, reviewed by an internal Carbon and Sustainability Steering Committee and published on our website.
On a bi-monthly basis it is reviewed by attendees of our public facing Environmental Sustainability Forum. |  |  |  |  | Action plan terms of reference
| Environmental Sustainability Actions and timetable | Update - Jan 2022 | Waste & Recycling | Land use, agriculture, biodiversity | Energy, water, resources | Housing & planning | Business & economic development | Transport
Action
1 | Make changes to the council's own premises, people and services we deliver
1.1 | Climate Declaration - Account for climate impacts in decision-making process | - | ü | ü | ü | ü | ü | ü
1.1.1 | Draw up carbon assessment tool to assess all council projects | COMPLETE - In use | ü | ü | ü | ü | ü | ü
1.1.2 | Undertake initial review of current EH sustainability purchasing statements included within existing service contracts to determine effectiveness and relevance. | COMPLETE - Our Contract Procedure Rules now ensure that procurement is conducted in a sustainable manner, taking environmental impact into account. The guidelines ask consideration of: do you really need it, can you specify a product service or works that is inherently more sustainable and that evaluation of the sustainability of the delivery of the goods works or service is undertaken. | ü | ü | ü | ü | ü | ü
1.1.3 | Engagement with main contractors to understand their current commitments towards carbon reduction | All carbon contributions from major contractors have been evaluated for our 2020/21 carbon total. In the main this covers our grounds maintenance and waste contracts. Our assessment covers fuel usage, utilities and water consumption via a structures audit template. The numbers we receive are then converted into carbon totals using universal conversion formulas so our reporting is reflective and comparable with other district authorities. Our next audit will commence again in April. In the meantime, we are working with our major contractors, where contract renewals allow, to continually improve carbon reduction initiatives. | ü | ü |  |  | ü
1.1.4 | Explicitly refer to sustainability outcomes in MTFP from 2020/21 budget onwards | COMPLETE - Now standard element of council's budget planning. | ü |  | ü | ü | ü | ü
1.1.5 | Amend the council’s procurement regulations to explicitly include consideration of carbon footprint (a) the determination of whether to procure (b) the specification for good and/or services to be procured and (c) the quality assessment of competing tenders. | COMPLETE - Contract procedure rules amended. | ü | ü | ü | ü | ü | ü
1.2 | Climate Declaration - Train members & officers to promote carbon neutral policies | - | ü | ü | ü | ü | ü | ü
1,2,1 | Train officers in climate change and sustainability through bite-sized training session. | 16 sessions have taken place with a total of 121 staff having been trained so far. Further sessions are being arranged in December and January. | ü | ü | ü | ü | ü | ü
1.2.2 | Train Senior Officers in climate change and use of carbon assessment methodology. | Senior Officers will be trained once the Officer training programme is complete. | ü | ü | ü | ü | ü | ü
1.2.3 | Offer Member training in sustainability and climate change. | Members will be trained once the Senior Officers training is complete. | ü | ü | ü | ü | ü | ü
1.2.4 | Visits to sustainability sites for the purpose of learning from best practice examples | Three site visits to sustainable landowner farms have now taken place with the last having taken place in November 21 by Cllr Graham McAndrew. More will be arranged. | ü | ü | ü | ü | ü | ü
1.3 | Carry out a staff survey to gather ideas for environmental sustainability | COMPLETE - 9 ideas were already in the Action Plan. Of the remainder, (24/69) 35% have been created as specific additional line items. The remainder, are already either complete, incorporated within a wider Action Plan line item or can be dealt with outside of the Action Plan. | ü |  | ü |  |  | ü
1.4 | WALLFIELDS - Target EPC rating C Within programme to increase minimum EPC rating of estate over the next three years. | Will not be progressed until after Agile Working building requirements are established. All staff are now working on a 50:50 home:office ratio from end of November 21 |  |  | ü
1.4.1 | WALLFIELDS - Audit to inform retrofit / re-fit programme | Will not be progressed until after Agile Working building requirements are established. All staff are now working on a 50:50 home:office ratio from end of November 21 |  |  | ü
1.4.2 | WALLFIELDS - Review and action repairs to improve insulation of windows | New action from staff survey. To be commenced alongside building requirements associated with Agile working |  |  | ü
1.4.3 | WALLFIELDS - Investigate opportunities for renewable energy generation | Will not be progressed until after Agile Working building requirements are established. All staff are now working on a 50:50 home:office ratio from end of November 21 |  |  | ü
1.4.4 | WALLFIELDS - Replace light fittings with LED | COMPLETE - Full replacement in December 2020. |  |  | ü
1.4.5 | WALLFIELDS - Review Local Authority decarbonisation grant scheme | COMPLETE - Investigated but oversubscribed. |  |  | ü
1.5 | BUNTINGFORD - Target EPC rating C Within programme to increase minimum EPC rating of estate over the next three years. | Possibilities were discussed with Facilities Management during a site visit in October 21. Further investigation required in order to form plans. |  |  | ü
1.5.1 | BUNTINGFORD - Audit to inform retrofit / re-fit programme | Possibilities were discussed with Facilities Management during a site visit in October 21. Further investigation required in order to form plans. |  |  | ü
1.5.2 | BUNTINGFORD - Replace light fittings with LED | All LEDs have now been replaced in the top shed and warehouses. Replacements in the office are nearing completion. |  |  | ü
1.5.3 | BUNTINGFORD - Investigate opportunities for renewable energy generation | Contract renewal in 2028 is unlikely to hinder sustainable investments and our landlord has positively responded our initial thoughts/enquiries. Solar panels on the Southern slopes of the two rooves would work well but further investigation of roof structure suitability would be required. Further possibilities include having air source heat pump units in cages on the sides of buildings. The possibility of moving to e-Refuse trucks also beings energy capacity and infrastructure at the site further into consideration. |  |  | ü
1.5.4 | BUNTINGFORD - Review Local Authority Decarbonisation Grant Scheme | COMPLETE - Investigated but oversubscribed. |  |  | ü
1.6 | CAR PARKS - Investigate carbon reduction and environmental opportunities. | 95% of all surface level carparks and lamp columns in parks have been fitted with energy efficient bulbs. G-Way MSCP and Jackson Square will be addressed on a replacement basis. The full project is part of our 5 year internal programme. |  |  | ü |  |  | ü
1.6.1 | Audit current numbers of/need for e-chargers across all carparks | COMPLETE - Audit information now informing installation works across all carparks. |  |  | ü |  |  | ü
1.6.2.0 | NORTHGATE END - (Bishop's Stortford) Investigate opportunities for installation of solar canopy on top deck. | COMPLETE - August 2021. Viability of taking this forward has been investigated. While there no plans at present to install a solar canopy, we will remain vigilant regarding inward investment opportunities to take this forward. |  |  | ü
1.6.2.1 | NORTHGATE END - Investigate opportunities for maximising sustainability during construction. | COMPLETE - May 2021 - A wet woodland incorporating over 300 shrubs and trees has been planted to the side of the car park providing biodiversity enhancement to the area. 54 e-chargers and LED lighting will be installed on completion. | ü |  | ü
1.6.2.2 | NORTHGATE END - Install e-chargers appropriate to demand identified during audit. | Northgate end will be a 597-space multi-storey car park once complete. 54 e-chargers are confirmed for installation. Completion is anticipated in early May 2022. |  |  | ü |  |  | ü
1.6.3 | GASCOYNE WAY - (Hertford) Install e-chargers appropriate to demand identified during audit. | 2 new fast chargers have now been installed bringing the total at the site to 6. |  |  | ü |  |  | ü
1.6.3.1 | GASCOYNE WAY - Green Wall | Project has previously been examined and external funding sought but unable to obtain. Opportunities for fresh funding are being kept under review but regrettably the criteria for DEFRA Air Quality Grant funding no longer support green walls. The Air Quality and Sustainability teams are working together to review ongoing possibilities.
1.6.4 | LINK ROAD - (Bishops Stortford) Install e-chargers appropriate to demand identified during audit. | The opportunity for chargers at Link Road has been investigated and is feasible and confirmation on future configuration of the site is being sought. |  |  | ü |  |  | ü
1.6.5 | BELL STREET - Install e-chargers appropriate to demand identified during audit. | COMPLETE - 2 chargers have now been installed. |  |  | ü |  |  | ü
1.7 | Investigate opportunities for use of 100% renewable energy for council estate | - |  |  | ü
1.7.1 | Investigate/procure 100% low-carbon electricity | COMPLETE - From 1st April 2021, when our energy accounts as part of CCS framework swap from British Gas (BG) to EDF, we will be placed on their Blue for Business tariff which used 100% low carbon energy. This exercise has gone partially beyond the original existing EDF contracts i.e. 19 rather than 4 contracts and includes the BG electricity contracts which are for smaller sites e.g. toilets, so is a positive move. The intention once further contract renegotiation is possible is to look to move to 100% renewable. |  |  | ü
1.7.2 | Investigate potential opportunity to procure 100% low carbon gas | Green Gas is gas from lower fossil fuels, i.e. waste biogas. It currently has limited availability in the UK. Evaluate again in 2022 |  |  | ü
1.7.3 | Install LEDs at all external lamp columns on Council's own estate. | 95% of all surface level carparks and lamp columns in parks have been fitted with energy efficient bulbs. G-Way MSCP and Jackson Square will be addressed on a replacement basis. The full project is part of our 5 year internal programme. |  |  | ü
1.8 | GRANGE PADDOCKS - Achieve BREEAM Excellent standard at new development | - |  |  | ü
1.8.1 | GRANGE PADDOCKS - Maximise environmental opportunities sustainability through the tender evaluation process. | COMPLETE - Tender specification fully reviewed |  |  | ü
1.8.2 | GRANGE PADDOCKS - Investigate opportunities for Solar PV installation | COMPLETE : These are now installed (April 2021) and producing 16.38kWhr at peak levels. |  |  | ü
1.8.3 | GRANGE PADDOCKS - Investigate opportunities for Heat Recovery | COMPLETE - 520kW has been calculated to be the instantaneous peak electrical demand of the leisure centre i.e. the maximum instantaneous electrical demand. 27% of this is an estimate of the typical minimum electrical demand. Therefore, 27% of 520kW = 140kW. The PV has a peak output of 16.38kW or 16.38 kilo-Joules per second (rate of flow of energy). The CHP (an electricity generator where the heat produced by the engine is recovered and can be used to heat the building) has a peak output, estimated at 50KW, given the calculation currently provided: total (PV+CHP) generation = 66.38kW. 520kW is likely to be an overestimate to ensure that there is enough supply. However, 140kW is more than twice 66.38kW, so it is unlikely that any significant amount of the generated electricity will need to be exported outside the building i.e. exported to the Grid Note if gas is no longer desirable for CHP it can be run off hydrogen in the future. |  |  | ü
1.84 | GRANGE PADDOCKS - Installation of EV charger(s) | 1 charging point with 2 car capacity in Car Park C has now been installed. Charging costs to the end user need to be agreed before activation. Provision (passive) for 7 more charging points in Car Park B |  |  | ü |  |  | ü
1.8.5 | GRANGE PADDOCKS - Review contractor utilisation of water, energy and resource use throughout the build process in line with BREEAM requirements. | COMPELTE - Grange Paddocks is now open to the public. Although there was no BREEAM requirement on the project, Environmental Sustainability contribution was tightly monitored. Construction Waste diverted from landfill and water consumption were consistently ahead of target. Energy consumption was slightly higher than target due to the required use of a generator as the permanent power became routed to the main building in the latter stage of the build. The main building is on a 'low carbon' energy tariff. As a whole, environmental performance ran at top marks (9/9) throughout. Excess carbon production will be offset by the carbon offset scheme used by the construction company. They have/will fund boreholes and low carbon stoves in Uganda and plant 10,000 trees during 2021. |  |  | ü
1.9 | HARTHAM - Achieve BREEAM Excellent standard for new development | Completion is programmed for December 2022. The building is being designed to reduce thermal gain (orientation and window location/sizes – passive design measures), lighting is specified to be very energy efficient (LEDs), and PVs and/or heat pumps will be specified which will provide a carbon reduction for the building. Meeting with the contractors to be arranged in early 2022 to start the contribution evaluation of each carbon reduction initiative. |  |  | ü
1.9.1 | HARTHAM - Maximise environmental sustainability opportunities through the tender evaluation process. | COMPLETE - Works commenced |  |  | ü
1.9.2 | HARTHAM - Calculate carbon reduction from reduced thermal gain | New sub action for further reporting. Meeting to be held with contractors in early 2022 to evaluate carbon reduction contributions of this initiative. |  |  | ü
1.9.3 | HARTHAM - Calculate carbon reduction from installing LEDs throughout | New sub action for further reporting. Meeting to be held with contractors in early 2022 to evaluate carbon reduction contributions of this initiative. |  |  | ü
1.9.4 | HARTHAM - Calculate carbon reduction from solar PV installation | New sub action for further reporting. Meeting to be held with contractors in early 2022 to evaluate carbon reduction contributions of this initiative. |  |  | ü
1.9.5 | HARTHAM - Calculate carbon reduction from air source heat pump installation | New sub action for further reporting. Meeting to be held with contractors in early 2022 to evaluate carbon reduction contributions of this initiative. |  |  | ü
1.9.6 | HARTHAM - Calculate carbon reduction from heat recovery technology | New sub action for further reporting. Meeting to be held with contractors in early 2022 to evaluate carbon reduction contributions of this initiative. |  |  | ü
1.9.7 | HARTHAM - Calculate carbon reduction from green wall installation | New sub action for further reporting. Meeting to be held with contractors in early 2022 to evaluate carbon reduction contributions of this initiative. |  |  | ü
1.9.8 | HARTHAM - Audit current number of/need for e-chargers and install more. | Arrangements for future EV charging are in place and implementation on the ground will be as the building programme permits. |  |  | ü |  |  | ü
1.10 | HERTFORD THEATRE - Achieve BREEAM Excellent standard for new development | BREEAM excellent rating is sought with an estimated 58% carbon emissions reduction anticipated on completion in 2023. Building energy use intensity will reduce 444 Wh/m2 per year to 260 Wh/m2 per year or, using benchmarking data, from 0.667kg to 0.334kg of CO2 per customer. These numbers are particularly significant as the building area, occupancy and energy consumption will increase when completed. |  |  | ü
1.10.1 | HERTFORD THEATRE - Maximise environmental sustainability through the planning and tender evaluation process. | Planning was granted in March 21. The tendeing pre qualification process is complete and we have now invited successful contractors to the full ITT stage. The ITTs will be returned by the end of January with a view to appointing a contractor by the end of February and commencing works in April 22. |  |  | ü
1.10.2 | HERTFORD THEATRE - Calculate carbon reduction replacement of gas boilers by air source heat pumps for heating/cooling. | New sub action for further reporting once contractor specification is known - early 22. |  |  | ü
1.11 | Maximise opportunity for EV - own and contract fleet | - | [5 empty] | ü
1.11.1 | Incentivise use of e-car pool by officers | COMPELTE - E-pool cars are now being used by officers and members of the public. A new, Covid-safe protocol is in place. Updated promotional material is also now on our website (Sept) | [5 empty] | ü
1.11.2 | Audit the council's vans with a view to replacing them with e-vehicles | The business case for replacement is now complete with the numbers, types and associated costs of new e-vehicles also agreed in principle. A meeting has also been held with the Energy Saving Trust regarding EV “fleet” comparison including larger (RCV) vehicle. | [5 empty] | ü
1.12 | Evaluate and monitor opportunities for sustainability improvements through East Herts Housing Association owned properties. | - |  |  | ü | ü
1.12.1 | Publish a new Housing Strategy for 2021 - 2026 incorporating environmental sustainability measures. | A new housing strategy will be presented to Full Council in December 21. It will contain a section on Housing and Sustainability. The Sustainability Team have been actively involved in its development. | ü | ü | ü | ü | ü | ü
1.12.2 | Millstream to conduct EPC ratings for existing housing stock. | All current EPCs for Millstream’s properties plus a list of energy efficiency works conducted to date are in the process of being collated. A possible "master action", to utilise Millstream to deliver carbon efficient development is under consideration. |  |  | ü | ü
1.12.3 | Undertake energy saving improvement at the Hillcrest Council- owned hostel | COMPLETE - All common parts and individual flats have been retrofitted with LED replacements in recent years. |  |  | ü | ü
1.12.4 | Undertake energy saving improvement at the Rectory Council- owned hostel | COMPLETE - Since the property was purchased in 2020, the main building has been improved by replacement hot water boilers, new thermostatic and on/off controls to existing radiators, LED lights throughout and movement sensors in all common parts. The Annex and Cedar Cottage (now converted into six new bedsits for single homeless people) has LED lights, two new gas boilers from a previous three, communal heating systems, replacement double glazing from single and thermal loft, floor and ceiling insulation. Revised EPC certificate requested to calculate savings. |  |  | ü | ü
1.12.5 | Monitor and report on Housing Association energy efficiency programmes | An energy efficiency programme is currently being undertaken with the 15 housing associations who build, own and/or manage housing stock in East Herts. High quality sustainable development standards are encouraged including the Housing Quality Mark (HQM) (equivalent to BREEAM) Passivhaus and Building Futures - an interactive Hertfordshire guide to promoting sustainability is in development. A record of all Associations' environmental sustainability actions is also being compiled. The Government’s Social Housing Decarbonisation Fund (SHDF) is also on radar with information being gathered on the possibilities contained within the Social Housing Retrofit Accelerator programme. |  |  | ü | ü
1.13 | Utilise Eastern New Energy ERDF Scheme to deliver innovative, low carbon sustainability projects. | Further meetings have been held with the University of East London who are leading the Eastern New Energy scheme. Various elements are underway such as a grant scheme for businesses in relation to energy and sustainability. We will be promoting these grants in the New Year 2022. |  |  | ü |  | ü
1.13.1 | Assess opportunities and possible benefits of establishing an energy 'White Label'. | Initial introductory meeting held with University of East London - project leads for Eastern New Energy. This is not progressing at the moment not least as the energy market and utility companies are in turmoil and white label schemes are suffering accordingly. |  |  | ü |  | ü
1.13.2 | Assess options for work in partnership to operate an energy services company to deliver potential carbon offset opportunities. | Initial introductory meeting held with University of East London - project leads for Eastern New Energy. The regional intitiative is under investigation. This is a 2021 - 23 scheme. Further promotion/reporting due shortly |  |  | ü |  | ü
1.14 | Continue to develop sustainable options for waste and recycling | - | ü |  |  |  |  | ü
1.14.1 | Work with Hertfordshire Waste Partnership partners and others to explore synergies of working across administrative boundaries | Pending contract change point in 23/24 | ü |  |  |  |  | ü
1.14.2 | Consider reducing domestic residual waste bins to 140 litre capacity to 'nudge' more recycling | To be explored with the new contracts in 2023/24. Looking at more efficient ways of collecting waste. The key action is to maximise gains from contract renewals. | ü
1.14.3 | Explore potential and practicality of electric refuse vehicles | We will be able to contractually change our fleet in 2025. Meantime investigations into the potential for and practicality of electric refuse vehicles are underway including breakeven/ round service mileage and depot energy capacity implications. A demonstration of an ECollect electric vehicle was arranged at our Buntingford depot in October 21. | ü |  |  |  |  | ü
1.15 | Assess evidence-base for benefits of green walls | COMPLETE - Incorporated into the Sustainability Supplementary Planning Document (SPD) which was passed at full council in March 2021. |  | ü | ü |  |  | ü
1.16 | Investigate opportunities for improving biodiversity of council estate and associated services. | We marked the launch of the Queens Canopy initiative on 24th May via a Council staff volunteering day, which saw us plant over 300 trees and shrubs at Northgate End in Bishop’s Stortford, creating a ‘wet woodland’ in the heart of the town. We will have a further staff tree planting day in January 22. Planning for further/larger tree planting and biodiversity gain initiatives on our own land is underway with audits of possibilities in our parks and open spaces and potential for leaving further district verges uncut for longer. These audits are due for completion by the end of 2021. |  | ü | ü
1.16.1 | Work with HCC and others to identify options for tree planting | A database of tree planting relating to the Queens Canopy is now administered by Hertfordshire County Council. Hertfordshire has a target for 3200 tree plantings shared equally between the 10 Local Authorities. East Herts is keeping a tally of tree plantings in district and is ahead of target. Work to promote the Queens canopy to Town and Parish Councils and community groups has also complete. Further opportunities will also come about once HCCSPs biodiversity land audit takes place. |  | ü
1.17 | Maximise environmental sustainability opportunities through Hertford Hydro | COMPLETE - The Executive Committee has now considered the updated business case for the Hydro and have determined that alternative investments elsewhere will be more beneficial to environmental sustainability and climate change progress. |  | ü | ü
1.18 | Maximise opportunities to utilise IT infrastructure (back and front end) to further carbon reduction. | - |  |  | ü
1.18.1 | Introduce video-conferencing technology in council buildings | COMPLETE - Q3 2020 |  |  | ü |  |  | ü
1.19 | Confirm Terms of Reference for Environmental Sustainability Corporate Group with a view to include wider sustainability issues beyond immediate carbon measures. | COMPLETE - Beyond carbon accounting, this Action Plan now incorporates the following terms : - Waste/Recycling - Land use/agriculture/Biodiversity - Energy/water/resources - Housing and planning - Business and Economic Development - Transport | ü | ü | ü | ü | ü | ü
1.20 | Incorporate HCCSP Water plans etc. | We have now received the final version of the HCCSP Water Plan and work is now underway to merge East Herts related actions into this plan |  |  | ü
1.21 | Work to improve biodiversity infrastructure on Council estate. | Environmental Sustainability and Biodiversity considerations are a core part of the Parks and Open Spaces Strategy 21-26, which will be approved/published in Jan 2022. Ongoing strategy work with CMS ensures all planned park projects optimise biodiversity as well as s106 contribution opportunities. The Queens Canopy initiative is being factored into the open space strategy. We are also mindful of the forthcoming HCCSP Biodiversity Audit and how that will inform required future schemes. |  | ü
1.21.1 | Incorporate relevant actions from HCCSP biodiversity Action Plan within this Action Plan. | We have now received the final version of the HCCSP Biodiversity Plan and work is now underway to merge East Herts related actions into this plan |  | ü
2 | Use regulatory powers to promote action by others
2.1 | Climate declaration - climate and sustainability friendly planning and building control regulations. Seek to develop appropriate planning policy to further establish climate change and sustainability ambitions. | - |  | ü | ü | ü
2.1.1 | Publish an Environmental Sustainability SPD | COMPLETE - March 21 - Agreed at Full Council and now published on East Herts Council website | ü | ü | ü | ü |  | ü
2.1.2 | Publish a Vehicle Parking Standards SPD | Production planning is underway for a new Vehicle Parking in New Development SPD (to replace the current Vehicle Parking Standards SPD) which will include requirements for vehicle charging points etc. The provisional timetable plans for consultation in late 21 with adoption in early 2022. |  |  | ü | ü |  | ü
2.1.3 | Publish a Biodiversity SPD. | Yet to commence. Planned for 2022 |  | ü |  | ü
2.1.4 | Publish a revised District Plan | A District Plan review has now started with a ‘call for sites’. | ü | ü | ü | ü | ü | ü
2.2 | Develop sustainability advice geared towards listed buildings / conservation areas | East Herts has over 4000 Listed Buildings. Meeting held with planning colleagues and all associated current guideline documentation now reviewed. A number of listed buildings are held by agricultural landowners in East Herts. An opportunity to connect planning with this community is under development for the next Rural Round Table. |  |  | ü | ü
2.3 | Survey locally active residential developers to better understand barriers to higher energy efficiency/Passivhaus development | COMPLETE - Results of this survey provided useful, ranked insights into the barriers to sustainable development. HCCSP Carbon Group is looking to develop actions around upskilling of contractors on a County-wide basis. |  |  | ü | ü
2.4 | Utilise s106 to maximise interventions in order to facilitate the Council's sustainability ambitions. | Work is progressing well on identifying potential sustainability opportunities (project themes and locations) that could be fulfilled via s106 contributions. In particular, investment in e-charging presents a significant opportunity. Meetings in group, and individual conversations have now taken place with Town and Parish Councils and Village Hall committees to advance the e-charging opportunity as a project linked to OZEV grant funding. | ü | ü | ü | ü | ü | ü
2.4.1 | Understanding the sign off process and ensuring sustainability gains in relation to the ambitions of the climate change Action Plan are facilitated in future s106 agreements | COMPLETE - All proposed planning permissions where s106 is triggered are now notified to Environmental Sustainability. The sign off process and stakeholders for the different types of allocations are known and work is underway to embed environmental sustainability personnel and factors more closely into the decision making process, potentially through the development of a check list. | ü | ü | ü | ü | ü | ü
2.4.2 | Investigate 'unallocated' sums with a view to working with recipients to provide guidance and encouragement to ensure use of funds is related as far as possible to sustainability ambitions of the Council. | Work is progressing well on identifying potential sustainability opportunities (project themes and locations) that could be fulfilled via s106 contributions. In particular, investment in e-charging presents a significant opportunity. Meetings in group, and individual conversations have now taken place with Town and Parish Councils and Village Hall committees to advance the e-charging opportunity as a project linked to OZEV grant funding. | ü | ü | ü | ü | ü | ü
2.4.3 | Produce 'shopping list' for actions which can be assisted and achieved through s106 agreements i.e. village hall improvements and e-charging | Meetings and 'sustainable shopping lists' will be developed (as a full project( upon completion of the analysis of existing s106 contribution potential. A first example of this type of initiative has now been delivered at Gilston Village Hall where a site visit enabled sustainability improvements to be identified, ranked and put foward for consideration. | ü | ü | ü | ü | ü | ü
2.4.4 | Work with HCC Transport to review existing funds/projects and future allocations to ensure facilitation of the Council's climate and sustainability ambitions with a joined up approach. | Our s106 Manager attends regularly scheduled meetings with HCC to ensure potential and existing project awareness around sustainability is ongoing. | [5 empty] | ü
2.5 | Maximise environmental sustainability through the Harlow Gilston Garden Town Development | - | ü | ü | ü | ü | ü | ü
2.5.1 | Identify and meet Harlow Gilston sustainability leads and develop co-ordinated action. | East Herts influence is predominantly around planning. Meeting held with Planning and legal colleagues around forwarding the sustainability agenda and wording development guidelines. In the meantime we will maintain a watching brief. | ü | ü | ü | ü | ü | ü
2.6 | Install anti-idling guidance/advisory signage in council carparks. | COMPLETE - A Clean Air Day campaign was rolled out across East Herts and materials shared with other Hertfordshire Local Authorities. 26 anti-idling signs were also installed in car parks across East Herts. |  |  | ü |  |  | ü
2.6.1 | Work with HCC on introducing enforcement measures in relation to anti-idling. | In contact with HCC. Potential for a county-wide campaign coming through HCCSP. East Herts have conducted their own research into the legalities and possibilities. |  |  | ü |  |  | ü
2.7 | Facilitate move to increased use of e-taxis through promotion of Herts 2025 EV Taxi Scheme. | COMPLETE - MHCLG has confirmed the ERDF scheme final go ahead and promotion, led by Electric Blue, is now underway with support from Herts Local Authorities. Local taxi cab individuals and companies can now lease an electric taxi for a trial period at a substancially subsidised rate for 6-12 months, with the option to purchase following the trial. |  |  | ü |  | ü | ü
2.7.1 | Install rapid e-chargers in support of move to more e-taxis. | Electric Blue are experiencing delays due to obtaining final government sign off of the the ERDF funding scheme. The focus is therefore not currently on rapid charging provision. Additionally this is also linked with development of Hertfordshire's county-wide electric vehicle strategy which is anticipated for agreement in the New Year 2022. East Herts has seen the first successful, fully electric taxi procured on a trial lease scheme through the ERDF funding support. |  |  | ü |  | ü | ü
2.7.2 | Review and update taxi vehicle policies to further strengthen incentives/requirements for low emission taxis | Currently being investigated by HCCSP transport group. |  |  | ü |  | ü | ü
2.8 | Work to utilise regulatory powers to facilitate improved domestic energy efficiency measures. | The 2021-26 Housing Strategy has aim to formally evaluate domestic EPC levels across the district, which will inform gaps and potential. All EPCs of housing coming to market are already regularly collected. A general trend of improvement has been noted. |  |  | ü
2.8.1 | Consider promoting improved EPC ratings through HMO licensing powers and policies. | Part of this action is being taken forward via the East Herts Housing Strategy 2021-2026 under the theme Housing Standards and Environmental Sustainability. The Clean Growth Strategy set a target to upgrade as many houses to EPC Band C by 2035 “where practical, cost-effective and affordable”, and for all fuel poor households, and as many rented homes as possible, to reach the same standard by 2030. A list of all HMO landlords, available in the public domain, will also be used for a direct marketing campaign promoting EPC improvements. |  |  | ü
| Explore a pilot to incentivise EPC A properties through the council tax system | COMPLETE - Reviewed and concluded not to take forward. Will retain for review. Determined other methods to incentivise domestic energy efficiency. |  |  | ü
3 | Influence and encourage others to do things
3.1 | Provide and promote energy efficiency grants/support | November 21 saw us launch the LAD2 grant for home sustainability improvements for low income households. A wide range of business grants are also available which we will promote throughout January 2022. Local enquiries for our loft and cavity wall scheme have also picked up again recently as the weather has turned colder. |  |  | ü
3.2 | Climate Declaration - Establish and run a multi-agency/stakeholder Environmental and Climate Forum meeting every two months and ensure Action Plan is updated on a monthly basis and made available to the public via our website. | COMPLETE - Now established and meeting every two months with different themes per meeting. The Action Plan is updated on a monthly basis and shared on our website. | ü | ü | ü | ü | ü | ü
3.3 | Enhance biodiversity infrastructure across the District | - |  | ü
3.3.1 | Work with community to explore and action tree planting | £125 per Town & Parish Council has been released by HCC for the Queens Canopy. Some interest has already been expressed and the funding, as well as trees available for free via the Woodland Trust, was also promoted at our most recent Town & Parish Council meeting in November. We are also receiving and processing a significant number of community and Members requests for tree planting on our own, highways and community land. |  | ü
3.3.1.1 | Investigate options to sign up to Queen's Canopy Project once officially launched in May. | COMPLETE - East Herts marked the launch of the Queens Canopy initiative on 24th May via a Council staff volunteering day. This saw us plant over 300 native trees and shrubs at Northgate End in Bishop’s Stortford, creating a ‘wet woodland’ in the heart of the town, accessible to everyone. Contact with HCC (who are holding a database of trees planted) is also established and work underway to publish further promotional information to Parish/Town Councils and community groups. |  | ü
3.3.1.2 | Consider opportunities to establish an 'adopt a tree pit' scheme. | Yet to commence. Will involve working with Highways and residents regarding adopting a tree outside their property. |  | ü
3.3.2 | Enable volunteers to come together on joint initiatives (information, co-ordination and training) | Community-led sustainability events took place in all the major towns across the district in the run up to COP26. EHC provided in excess of £3,000 grant funding towards these events and is now working with groups to faciliate their actions plans and support ongoing community engagement by creating an inter-town skills network whereby we can connect people and ideas. The monthly Get Involved calendar on our website continues to provide events and ideas for community groups and individuals. We are also progressing with ideas to extend the scope of the Eat Herts Environmental Forum to enable commuity action facilitation, co-ordination and support. |  | ü
3.3.2.1 | Consider opportunities to establish community wildlife areas, for example, adjacent to play areas | In November 21 we invited residents to join us to finish off the planting at the improved play area at Trinity Close. With the help of young volunteers, Groundwork East and Glendale, we planted: 4 Trees, 2056 Shrubs and 256 Bulbs. Further work will be informed following the return of CMS's audit on our parks and open spaces. |  | ü
3.3.2.2 | Work with Parish Councils to promote local biodiversity action. | The intention for East Herts to take a greater co-ordinating role in sustainability matters was introduced at the first Town & Parish Council Engagement Event in June and was repeated at the second event in November 21. Engagement to date is predominently around promotion of the Queens Canopy initiative, rural e-charging provision and the request that each council take part in communicating sustainability calls to action and campaigns via Social media. |  | ü
3.3.2.3 | Work with HCC to ensure appropriate management of highways verges for biodiversity. | Some verges are now not mowed where safety permits. Further work to be informed by the HCCSP biodiversity audit. |  | ü
3.4 | Establish improved dialogue with rural and farming community | - |  | ü
3.4.1 | Establish and run a Rural Round Table bringing together key stakeholders in the farming and land holding/owning community. | The first Rural Round Table was held in February 21. A date will be set for a second meeting once objectives taken from completed HCCSP Action Plans can be included in the agenda. |  | ü
3.5 | Climate declaration Call on National Government for more powers and resources | - | ü | ü | ü | ü | ü | ü
3.5.1 | Write to ministers to initiate dialogue about powers and freedoms to support delivery of climate change commitments | COMPLETE - The Leader of the Council wrote to the Secretary of State in January 2020 requesting further support in achieving the stated climate change aims. | ü | ü | ü | ü | ü | ü
3.5.2 | Work with local MPs to promote the case for investment in sustainability interventions in East Herts | Officers met with two local MPs. Future meetings to be organised in due course. | ü | ü | ü | ü | ü | ü
3.6 | Climate Declaration - Work with partners - District, County and Region | Hertfordshire Climate Change and Sustainability Partnership (HCCSP) Biodiversity, Carbon, Transport and Water plans are complete and in the process of being integrated in to the East Herts Action Plan. | ü | ü | ü | ü | ü | ü
3.7 | Run EV roadshows and demonstrations - at least one a year | An e-car and e-bicycle display was made available at the Hertford and our Changing Climate event on 25th September 21 in Hertford town centre. |  |  | ü |  |  | ü
3.8 | Run two climate change film festivals (Hertford and Stortford) | Screening of the sustainability film 'Tomorrow' has now taken place in Bishop's Stortford, Sawbridgeworth and Ware with funding assistance via Grants provided by East Herts Council. | ü | ü | ü | ü | ü | ü
3.9 | Install more bicycle racks in the five market towns | COMPLETE - The three, two tier cycle racks originally sited in Hertford, Buntingford and Bishop’s Stortford have had to be relocated to support school community active travel for students and staff resulting in Richard Hale, Ward Freman and Bishop’s Stortford High School being pleased to accept these 16 bike rack storage facilities. Sawbridgeworth Cycle rack in Bell Street is in the process of being made more accessible and will be repositioned slightly to enable this. The new Ware site at Burgage Lane is being re-purposed to accommodate the rack, enabling good travel connections with the new medical centre, Ware High Street and the canal cycleways. | [5 empty] | ü
3.10 | Incentivise the public to make more use of the council e-car pool | COMPLETE - The scheme has now been fully re-opened to the public and promotion is now in place on our website. |  |  | ü |  |  | ü
3.11 | Hold a Schools Climate Conference | Now Covid restrictions are lifting, development of ideas are recommencing. This action was originally postponed until 2022 but the team have started remote re-engagement with schools via campaigns around Clean Air Day, ModeSHIFT Stars, World Car Free Day, Great Big Green week and tips for getting children involved with carbon and waste reduction and sustainability initiatives. | ü | ü | ü | ü |  | ü
3.12 | Work with Bishop's Stortford BID and other business groups to promote sustainability | Meeting held with Bishop Stortford's BID Manager on 8th September 21. A joint campaign has now been rolled out to promote sustainability related grants for businesses (Business Climate Hub, Workplace Charging Scheme, Low Carbon Workspace campaign and the Eastern Energy Grant) via direct email, web and social media channels. BID report that these has already been interest in some of the grants promoted. |  |  |  |  | ü
3.13 | Create East Herts awards scheme to encourage local organisations, neighbourhoods and individuals to implement sustainable activities | This action will take the form of a public pledge request, communicated via our own channels and via those available through our Town and Parish Council's, sustainability and community groups. | ü | ü | ü | ü | ü | ü
3.14 | Actively implement and encourage waste minimisation initiatives | International Compost Awareness Week, Love Parks (Keep Britain Tidy) and Plastic Free July were promoted via our Get Involved calendar. The July' Environmental and Climate Forum covered Waste and Recycling and Recycling in September 21. The East Herts' Master Composting (Waste Warriors) initiative has generated an encouraging number of community volunteers now specifically trained in food waste reduction and promotion and they have represented East Herts at all sustainability/COP related events across the District. | ü
3.15 | Hertford Subways AQMA project | COMPLETE - Subways now opened. Some minor works to be completed e.g. relocation of the litter bin. | [5 empty] | ü
3.16 | PARISH COUNCILS AND VILLAGE HALLS - explore creation of rural EV charging hub network based on parish owned sites | A formal project, which combines the oportunities presented by s106 funding and the OZEV grant, is now underway. |  |  | ü |  |  | ü
3.17 | Work with Parish Councils and Village Halls on sustainability initiatives | The intention for East Herts to take a greater co-ordinating role in sustainability matters was introduced at the first Town & Parish Council Engagement Event in June and was repeated at the second event in November 21. Engagement to date is predominently around promotion of the Queens Canopy initiative, rural e-charging provision and the request that each council take part in communicating sustainability calls to action and campaigns via Social media. |  | ü | ü |  |  | ü
3.17.1 | Explore creation of 'sustainable shopping list' for village hall equipment upgrades where s106 funding exists. | Now potential project themes and town/village locations have been identified we have the framework for a shopping list. |  |  | ü |  |  | ü
3.17.2 | Integrate sustainability topics within the agenda for East Herts Parish Councillors Conference. | COMPLETE - The sustainability topic has now been confirmed as a regular entry on the agenda at this meeting. | ü | ü | ü | ü | ü | ü
3.20 | Smart approach to publicity | A schedule of blogs, written by members of our sustainability working group, is now published monthly via our internal communications email and stored on our Intranet. A staff survey which took place in September/October also explored staff interest in different areas of environmental sustainability, and which will enable targeted staff engagement so that we can deliver the Sustainable part of SEED - 'sustainability being at the heart of everything we do.' Our Clean Air Day campaign touched 11,000 residents and had a 6 times greater rate of engagement than other recent social media posts. A next wave of promotion covering sustainability grants and initiatives for businesses and domestic heat initiatives is underway. A communication working party is also set up including members of the HCC Behaviour Change and Sustainability Communication teams. | ü | ü | ü | ü | ü | ü
3.20.1 | Review and expand web site pages on environmental sustainability, climate change and energy efficiency to provide enhanced advice and encourage behaviour change to promote positive climate action | Analysis of web-visitor metrics to the sustainability pages is now complete. Further work is underway to enable more granular reporting and uplift to visitor numbers. Sustainability is now accessible from the East Herts home page. Our carbon progress totaliser will be made public along with more in-depth detail of the council's own and wider district carbon totals and priorities. The hints and tips section will be expanded, more grants promoted and stronger links to Health & Wellbing and Recycling will be made. The use of social media will also be increased. | ü | ü | ü | ü | ü | ü
3.20.2 | Use social media more effectively to encourage behaviour change | A next wave of promotion covering sustainability grants and initiatives for businesses and domestic heat initiatives is underway. A communication working party is also set up including members of the HCC Behaviour Change and Sustainability Communication teams. | ü | ü | ü | ü | ü | ü
3.20.3 | Pursue possibilities to use digital signage in towns with this facility for behaviour change promotion in relation to water, idling et al. | There are no signs owned by East Herts Council Town & Parish Councils or Bishop Stortford BID. Investigations into the opportunities will be progressed with HCC Highways. |  |  | ü |  |  | ü
3.20.4 | Investigate use of database collected during brown bin change communications. | The next round of East Herts resident communications will take place in early 2022. Preparation to capture Opt In information is underway. | ü | ü | ü | ü | ü | ü
3.21 | Review heat recovery initiatives in the domestic sector. | Project is under initial development |  |  | ü | ü
3.32 | Promote COP26 | COMPLETE - Sustainability and Climate Action groups across our district’s towns have brought together some fantastic COP26 events including street stalls, presentations, film screenings and workshops. We’re extremely grateful and proud to acknowledge the extraordinary voluntary contributions of our local residents towards this cause. Thank you! Hertfordshire County Council are also holding an Eco Fair at County Hall on 27th November which we are promoting to our networks (call for exhibitors and attendees) | ü | ü | ü | ü | ü | ü